Section 7.  Terms of Reference

"Consultancy Services for Preparation of Conceptual Design, Bidding Documents and Procurement Support for Output and Performance Based Road Contracting (OPBRC) Civil Works in N1 Corridor"

Package 2: Gorongosa – Caia Lot 2 (84 -168 km) and Metoro – Pemba (0 - 94 km), in Sofala and Cabo Delgado Provinces under Design, Build, Maintain and Transfer Methodology

Contents

1.	INTRODUCTION	5

2.	KEY OBJECTIVES	5

3.	SCOPE OF THE SERVICES	8

3.1	General	8

3.2	Phase 1-1: Development of Contract Strategy	8

Task 1-1:  Definition of service level classification.	8

Task 1-2:  Cost Benefit Analysis	9

Task 1-3:  Financial Model to be used in design of the Mandatory Payment Schedule	9

Task 1-4:  Review of the contracting capacity to undertake and manage the works	10

Task 1-5:  Development of contract format	10

Task 1-6:  Industry Consultation Workshop	12

Task 1-7:  Development of a comprehensive approach to allocation and mitigation of Project Risks	12

3.3	Phase 1-2:  Review of the Existing Engineering Design	14

Task 2-1:  Review the Adequacy of Existing Design Documents and Information	14

Task 2-2:  Carry out additional technical surveys and site investigations	17

Task 2-3:  Climate Vulnerability Risk Assessment (CVRA)	17

Task 2-4:  Road Safety Assessment/Appraisal	18

Task 2-5:  Identification of E&S Requirements relevant for the Development of the Conceptual Design	18

3.4	Phase 1-3:  Preparation of Conceptual Design and Bidding documents	19

Task 3-1: Definition of service levels of the road.	19

Task 3-2:  Conceptual Designs, Financial Model/payment Schedule and Confidential Price Estimate for Civil Works Contract (Package).	19

Task 3-3:  Integration of E&S Requirements in Development of the Conceptual Design	22

Task 3-4:  Estimate and Pricing for Emergency Works	23

Task 3-5:  Preparation of Contract Documentation (Draft and Final Conceptual Design Reports and Draft and Final Bidding Documents).	23

3.6	Phase 2:  Support to the procurement process  until the award of contract;	24

Task 4-1:  Prequalification of Contractors	24

Task 4-2:  Pre-bid workshops	24

Task 4-3:  Tender Process and Evaluation of Tenders 	25

4.	DURATION OF THE ASSIGNMENT AND REQUIRED INPUT	25

4.1	Duration and Input for Phases 1 and 2	25

5.	REPORTS TO BE SUBMITTED	26

5.1	Reports Related to Phases 1 and 2 of the Assignment	26

6.	TEAM COMPOSITION	28

6.1	Team Composition for Phase 1 and 2	28

6.1	Staff Qualifications Phase 1 and 2	29

7.	DATA, FACILITIES AND RESOURCES TO BE PROVIDED BY THE EMPLOYER	33

8.	CONSULTANT’S OBLIGATIONS	33

General	33

Transportation Requirements	33

Staff Housing	33

Offices for Consultant’s personnel	33

Travel Related Costs and Allowances for Consultant’s personnel	33

Road Surveys	33

Reimbursable Expenditure	34

9.	LOGISTICAL SUPPORT	34

Liaison Officer	34

10	LOCAL TAXES	34

11.	PAYMENT SCHEDULE	34

ANNEX 1: LOCALITY MAP	36

# 1.	INTRODUCTION

The N1 between Maputo and Pemba was identified as the priority road corridor in the 2001 Road Sector Strategy, and interventions on prioritized sections of the road started in 2004. N1 is the key spine of the primary national road network and the most important transport corridor for Mozambique in order to unlock development potential (in all sectors) in central and northern Mozambique, the latter being the country’s most fragile and critical region. It is also part of the SADC identified strategic regional road network aimed at providing a cross-border trade network within the Southern African region. In this light, the Government of Mozambique (GOM) requested the World Bank (the Bank) help develop a –long-term program of socio-economic integration through resilient and safe upgrading of the N1 corridor.

The World Bank has agreed to prepare a US$850 million Multiphase Programmatic Approach (MPA) operation over three International Development Association (IDA) cycles, with a first phase approved in August 2022 for $400 million to be implemented between 2022 - 2032, with subsequent Phases II and III planned for delivery from FY2026 to2032 to finance a Safer Road for Social and Economic Integration Project in Mozambique (SRSEIP or the Project) to implemented along the N1 corridor. The MPA for SRSEIP will support a resilient and safer upgrading of about 1,053 km of priority sections out of the total 2,477 km length of the N1 – corridor.  It is estimated that the proposed project will connect more than 5 million people to the rest of the country and better integrate them into the national economy.

Seeking to increase the efficiency and effectiveness with which the management and maintenance of the road network is carried out, the Government of Mozambique, through Administração Nacional de Estradas (ANE), intends to combine the well-known and traditional methods of road rehabilitation and maintenance contracting with new concepts and instruments for the management of a part of the national road network.

The main objectives of these consultancy services are to assist ANE in its objective to upgrade the N1 Road infrastructure to climate resilient standards and build a safer transport corridor. The selected consultant will prepare conceptual engineering design of prioritized sections of the N1- Corridor, assist the procurement of the output- and performance-based road contracts (OPBRC) and identify future developments based on lessons learnt from these services during different phases. These services will be undertaken as part of SRSEI -MPA.

These Terms of Reference (ToR) describe the nature and scope of the services to be provided by the consultant.

# 2.	KEY OBJECTIVES

The development objective of the Project is to improve road connectivity, safety, and climate resilience and develop social inclusion in the Project areas. This ToR is valid for each of the packages (lots) listed in Table 1.

The rehabilitation/upgrading of the Priority Road sections will be implemented over a period of 10 years divided in three separate phases of the MPA. The interventions will include among others, pavement rehabilitation, rehabilitation or reconstruction of drainage structures such us bridges and culverts, improvement of intersections, rehabilitation/upgrading of road safety facilities followed by road maintenance.

The Project will be packaged in lots along N1 as detailed in the table below, considering differences in their locations [and existing conditions]. Works on each lot comprise (i) rehabilitation during the first 2-3 years, (ii) regular routine maintenance, and (iii) periodic maintenance towards the end of the contract period (suggested in the 9th year or later) for improvement of the condition

The client has the feasibility studies and detailed engineering designs for most of the sections identified in Table 1 below. These studies were completed between 2010 and 2016 in anticipation of potential inclusion in one of the earlier Bank financed operations.

| Concept Design Consultancy Contracts (Packages) | MPA Phase | Road Sections / OPBRC Civil Works Contracts | Km | Province | Procurement Concept Design Services | Preparation of Concept Design | Procurement OPBRC Works | Availability of Engineering Designs (Year) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Package 1 (154 km) | 1 | Inchope – Gorongosa | 70 | Sofala | 2023 | 2023 | 2023 | Yes (2016) |
|  | 1 | Gorongosa - Caia Lot 1 (0-84 km) | 84 | Sofala | 2023 | 2023 | 2023 | Yes (2016) |
| Package 2 (178 km) | 1 | Gorongosa - Caia Lot 2 (84-168 km) | 84 | Sofala | 2023 | 2023 | 2023 | Yes (2016) |
|  | 1 | Metoro – Pemba | 94 | Cabo Delgado | 2023 | 2023 | 2023 | Not available |
| Package 3 (176 km) | 1 | Chimuara – Nicoadala Lot 1 (0-88 km) | 88 | Zambézia | 2023 | 2023 | 2023 | Yes (2010) |
|  | 1 | Chimuara – Nicoadala Lot 2 (88-176 km) | 88 | Zambézia | 2023 | 2023 | 2023 | Yes (2010) |
| Package 4 (158 km) | 2 | Gorongosa - Caia Lot 3 (168-252 km) | 84 | Sofala | 2024 | 2024/25 | 2025 | Yes (2016) |
|  | 2 | Rio Lurio – Metoro, incl. bridge Rio Lurio | 74 | Cabo Delgado | 2024 | 2024/25 | 2025 | Yes (2010) |
| Package 5 (187.5 km) | 2 | Muxungue – Inchope Lot 1 (0-77.5 km) | 77.5 | Sofala | 2024 | 2024/25 | 2025 | Not available |
|  | 2 | Rio Save – Muxungue | 110 | Sofala | 2024 | 2024/25 | 2025 | Yes (2016) |
| Package 6 (199.5 km) | 3 | Pambarra - Rio Save | 122 | Inhambane | 2027 | 2026/27 | 2027 | Yes (2015) |
|  | 3 | Muxungue – Inchope Lot 2 (77.5-155 km) | 77.5 | Sofala | 2027 | 2026/27 | 2027 | Not available |
|  |  | Total | 1,053 |  |  |  |  |  |

Table 1: Priority Sections of N1 Corridor

Most of the above referred sections already have engineering studies for rehabilitation using conventional contracting methods (Design, bid, build basis), except for Pambarra - Rio Save which already has a conceptual design for rehabilitation and maintenance using OPBRC contracting method. For the sections Muxúngue – Inchope (Lot 1 and Lot 2) and Metoro - Pemba no engineering designs are available.

The concept design documents for the roads listed in the above table 1, will be updated to ensure compliance with design standards and specifications prepared recently for ANE as referenced below.

ANE Standards and Specifications

| 1. | Field and Laboratory Testing Manual, 2020 |
| --- | --- |
| 2. | Geometric Design Manual, 2019 |
| 3. | Geotechnical Design Manual, 2020 |
| 4. | Hydrology and Drainage Design Manual, 2019 |
| 5. | Pavement Design Manual, 2019 |
| 6. | Performance Specifications – OPBRC Manual, 2019 |
| 7. | Rehabilitation Design Manual, 2019 |
| 8. | Specifications for Bridge Loads, 2019 |
| 9. | Standard Details for Roads and Bridges, 2020 |
| 10. | Standard Specifications for Road and Bridge Works, 2020 |
| 11. | Site Investigations for Road and Bridge Works, 2019 |

Those standards and specifications are available at ANE – Headquarter. These standards will be complemented by the regional Southern African Development Community (SADC) standards in use, as published by the Southern African Transport and Communication Commission (SATCC), September 1998 (Reprinted July 2001). Due consideration shall also be given to the SADC Road Traffic Signs Manuals.  In the absence of appropriate standards covered by the documents listed above the consultant should recommend and adopt recognized international standards in agreement with client.

The concept engineering designs must also focus on the government aspirations in achieving SDG 3.6 of decreasing the number of road crashes fatalities by 50 percent by 2030. In Mozambique, during the period 2011 – 2019, 22.385 road crashes were recorded which resulted in 53.359 victims, of which 13.500 fatalities .

# 3.	SCOPE OF THE SERVICES

## 3.1	General

The objectives of these services are:

- To prepare a concept stage engineering designs, which will be a basis for a prospective contractor to develop detailed engineering designs under the OPBRC concept;

- Prepare OPBRC bidding documents and assist ANE in the procurement of OPBRC Contractors;

- identify future developments based on lessons learnt during different phases of this assignment.

ANE wishes to employ a consultant to assist in preparing the concept engineering designs and OPBRC bidding documents and to provide support during the procurement of works contracts. The services are divided into two phases, namely:

Phase 1:

Phase 1-1: Development of Contracting Strategy (including slice and packaging approach as well as combining rehabilitation and maintenance)

Phase 1-2: Review of the adequacy of existing information and studies and collection of additional data especially to conduct a climate vulnerability risk assessment (CVRA) and Road Safety Audit.

Phase 1-3: Preparation of Conceptual Designs, Financial Model/Payment Schedule and Confidential Price Estimate for Civil Works Contracts, and Integration of Environmental and Social (E&S) requirements in the development of the conceptual designs and bidding documents;

Phase 2: Support to the Procurement Process until the award of contract;

The Consultant is expected undertake necessary improvements to the existing detailed engineering designs (where  available) to ensure upgraded road safety and resilient infrastructures,  their cost-efficiency and prepare the Concept Designs for OPBRC contracts. The contracts for the works within the project shall be based on the World Bank’s Sample Bidding Document “Procurement of Works and Services under Output and Performance Based Road Contracts, April 2021.  This document is available on the World Bank's website under https://thedocs.worldbank.org/en/doc/0a3444f756c0adf8dd5e88527f9a1877-0290032021/original/Sample-Specs-OPBRC-April-2021.docx.

Consultants can submit proposals for one or more packages  listed in the REOI.

## 3.2	Phase 1-1: Development of Contract Strategy

### Task 1-1:  Definition of service level classification.

The Consultant will define a generic system of service level classifications appropriate for the type and function of the road as per Mozambique road classification system and related design standards. The service level will be defined mostly from the road user’s point of view. They should be simple and easy to evaluate and take into consideration the criteria provided in the Technical Specifications of the World Bank’s Sample Bidding document for OPBRC (travel speed, comfort, etc.). Criteria may however be added or dropped as needed in the specific country context.

It is important to note that the Consultant is expected to fine-tune the service level parameters and recommend a system which provides an appropriate balance between economic considerations and sustainable service conditions for both the client and for the road users keeping in mind the current and projected traffic load and the need to provide consistent service levels over the entire N1 corridor and rest of the primary road network. For the execution of this task, the Consultant will carry out consultations with different types of road users representing the different traffic and vehicle types (both motorized and non-motorized, and including pedestrians).

The Consultant shall also define method and systems required by the public/road users in informing the authorities on road condition.  The system will then be used in evaluation of contractor’s performance.

The Consultant shall also review potential data collection systems and develop proposals for innovative methods of involving the road users and the wider public to inform the responsible road authorities regarding the road condition and service levels being achieved.  The system is intended to be used in the evaluation of contractor’s performance and consequently the calculation of his payment for the relevant period.

### Task 1-2:  Cost Benefit Analysis

The Consultant shall carry out a cost benefit analysis for the proposed engineering options including a sensitivity analysis, to substantiate the best “value for money” option chosen for the implementation.

### Task 1-3:  Financial Model to be used in design of the Mandatory Payment Schedule

Based on the service level classification established under Task 1.1 above, the Consultant will carry out a detailed analysis which will lead to an estimate of the likely medium and long-term cost of assuring each of the pre-defined service levels.  In order to reach that conclusion, he will need to identify all physical works and other activities (managerial, quality control, etc.) that the contractor will most likely have to carry out for each service level class, as well as the frequency of those activities and interventions and taking into consideration the expected condition of the road at the time of handing over to the Client at the end of the contract.

The consultant should develop at least three alternatives for cost recovery models so as to define the most suitable and optimized method for calculating the payment to the Contractor, as well as to identify “the best value for money” option. The cost estimate will be based on conceptual designs for each road which will include the typical cross sections and other typical geometric and pavement design parameters. The Consultant will be required to carry out an updated traffic count survey along the project road length.

At this stage the cost estimate will be based on a market analysis of similar road rehabilitation and improvement works in Mozambique over the last 5 years, including those carried out under OPBRC.

The financial model for each of the options should show the cash flow projections requirements for the OPBRC Contract and shall be structured in such a way that a part of the payments for rehabilitation and upgrading is deferred to the maintenance performance period to ensure that the contractor remains committed throughout the entire contract period and pays sufficient attention to the maintenance. The Consultant may explore the option(s) of using Bank Guarantee(s) to improve the cash flows of the Contractor.

### Task 1-4:  Review of the contracting capacity to undertake and manage the works

A general assessment on contracting and consulting capacity at the level of ANE has confirmed that there is scope for introducing performance-based contracting in Mozambique. However, a more detailed assessment of technical (specifically, design and long-term maintenance planning capability); financial and managerial capacity shall be undertaken to identify:

- The number of potential bidders for such work;

- Specific issues of risk which will require mitigation when developing the contract documents and

- The value of contract/(s) packages and phasing that will best fit foreign and local capacity.

The review shall consider both the consulting and contracting industry and include awareness-raising activities to inform the market of the opportunities presented by these contracts and assess levels of interests and concerns expressed by the industry.

It should be noted that ANE experience of OPBRC work is increasing through a current contract for the rehabilitation and upgrading of sections of N1/N10 road in Zambézia province and past Design and Build road contracts in in Gaza province.  Lessons learnt from that contract will benefit the preparation of documents under these TORs.  ANE will aim to facilitate this dialogue at the appropriate time.

### Task 1-5:  Development of contract format

The Consultants shall refer to (Sample Specification for OPBRC, April 2021) annex  to World Bank Standard Procurement Document for the OPBRC  and recommend an appropriate format for the Project. It is important that the proposed format matches the industry’s ability to undertake the works and maximizes the potential for success.

Issues to be addressed include the extent of the assets, in addition to the pavement to be maintained under the contract, for example, in addition to the pavements should the contract include the management and maintenance of all:

- Signage.

- Delineation.

- Lighting.

- Vegetation.

- Bus/heavy vehicles rest stops.

- Slopes.

- Retaining Structures.

- Drainage Works.

- Bridge Structures.

- Non-motorized traffic facilities

- Ambulance units

- Road Right of Way. (i.e. control and preservation)

At the completion of this task the Consultant shall prepare a concise report outlining the options considered, the reasons for their recommendations, and the cost implications.

The Consultant shall give careful consideration to the appropriate mix of output elements in the contract, to get best value-for-money during the entire operation/duration of the project life, which will encompass the rehabilitation, maintenance, and surface renewal (periodic maintenance) before handing over the facility back to the Client.

The overall environmental and social risk classification of the Project is High; the environmental risk is Substantial while the social risk is rated as High. Following the World Bank Environmental and Social Framework’s requirements, the SPD OPBRC format needs to integrate the E&S requirements applicable to MPA SRSEI (namely mitigation measures and monitoring and reporting procedures) as per the E&S instruments prepared for the project, which include: Environmental and Social Management Framework (ESMF), Environmental and Social Impact Assessment study (ESIA)/Environmental and Social Management Plan (ESMP), Resettlement Policy Framework (RPF), Resettlement Action Plan (RAP), Stakeholder Engagement Plan (SEP) (including a GBV/SEA/SH sensitive Grievance Redress Mechanism (GRM)), Labour Management Procedures (LMP) (including a GRM for the project workers), Social Assessment (SA), and Gender-based Violence (GBV) risk assessment [including Sexual Exploitation and Abuse (SEA) and Sexual Harassment (SH)].

Annex 9 of the ESMF provides a preliminary set of Environmental and Social Clauses to be considered and updated with the relevant data upon inclusion in the OPBRC format.

End of the contract  residual life of the road. To ensure that the road is returned to the client in a condition defined by the contract and that will not require any major capital investments in periodic maintenance immediately following the end of the contract, the Consultants shall specify separate residual life for key element of the project road.

The Consultants shall review, as a part of this assignment, the expected impact of the OPBRC in terms of asset value up to the end of the contract and should advise the Client on the inclusion of additional measures during the contract period to maximize the asset value at the end of the contract, including among others, the indicative timing of periodic maintenance.

The Consultant shall also specify procedure for arrangements in the contract for detailed joint inspections about one year prior to hand over of the roads to be carried out by the ANE and the contractor.  In these inspections likely works needed are noted and remedial action is expected to be taken in accordance with an agreed plan.  For compliance of the agreed plan, another inspection shall be carried out no later than six months prior to the end of the contract. A similar procedure covering all elements of the project road may be specified prior to the end of the contract to ensure work has been carried out in accordance with the agreed program and to assess any other works needed to achieve the required standard at contract termination. In addition to the standard performance guarantee, the Consultant shall also suggest a financial arrangement such as retention money or depositing the suitable percentage of the amount of agreed remedial works in an escrow account which ANE may utilize if the contractor fails to complete the work.

The Consultant shall prepare a compliance framework for ensuring compliance of the works, including the penalty regime that will prevail in the event of any non-compliance by the contractor. This will also include methods and systems involving public/road user interactions related to road situation/condition.

The bidding evaluation procedures: The Consultants shall work with ANE to develop an evaluation procedure that meets the objectives of obtaining the best value for money over the term of the contract, whilst at the same time providing sufficient flexibility to the bidders to be innovative in the provision of the civil works and cost effective road asset management practice whilst complying with the legislative requirements that govern the letting of contracts by ANE.

### Task 1-6:  Industry Consultation Workshop

The Consultants shall organize and conduct one “approach-to-market” workshop with representatives from the industry (contractors, consultants and other interested parties) to outline the draft contract strategy and gain their feedback before producing the Final Report and Draft Bidding Documents.

### Task 1-7:  Development of a comprehensive approach to allocation and mitigation of Project Risks

The Risks allocation Matrix is a  key component of OPBRCs. The Consultants shall identify all associated risks related to the proposed OPBRC, analyze them, quantify them, and prepare the cost estimates in the table format. Each risk will be analyzed and allocated to respective party which is best able to manage the risk. Unallocated risk and the risk allocated to ANE will be covered under Provisional Sum in the Contract, which can be utilized only with a specific approval of the client. Some of the risks identified initially, but not limited to, are:

- Detailed Design Phase. These involve potential challenges with conducting field investigations and their ramifications for detailed designs, for instance the requirement to carry out demining operations and the removal of unexploded ordnance.

- Inflation.  The contracting industry has concerns with bidding for a long term contract if they are not to be adequately protected against inflation and exchange rate fluctuation.  An index for escalation during the contract shall need to be developed to mitigate the risk.

- Traffic growth.  Traffic levels have a significant impact on the price of the contract in terms of the degree of damage caused to the pavements.  The approach can be to place the risk of traffic growth with the contractor, up to a threshold value beyond which the client compensates the effect of additional growth.

- Traffic overloading.  Mozambique has a significant problem with overloaded trucks using the network.  Since overloading has a significant impact on the price, the consultant should consider the most recent GOM policy/legislation and make recommendations for mitigating this issue.

- Emergencies and natural hazards (e.g. slip/breach etc.).  The approach to managing emergencies will need to be covered in the OPBRC contract.  Various methods have been used elsewhere for such items – open book accounting, coverage of work up to a certain value by the contractor above which the client makes extra payment, or rate fixing at market rates – and each have their advantages and disadvantages.

- Construction Phase: Upgrading/Rehabilitation works and future potential development work.  These risks are both similar and complex involving a period during the construction implementation, for instance the cost and possible implementation delays related to the removal of public utilities such as telecommunication lines including fiber optical cables, power supply, water supply,  etc.   The approach to share a much information as possible and keep a provisional sum to cover the cost of removal of such utilities.

- Environmental and Mining licenses: The Ministry of Mining issues all mining licenses in Mozambique. Similarly, Ministry of Environment is tasked with issuance of environmental licenses after the provincial authorities have cleared it. Previous projects have faced consistent delay in issuance of these licenses. Appropriate approach to mitigate the delay risk needs to be designed.

- Change in Law. Change in law can cause   a significant impact on the cost or reduction in net after tax return or other financial burden.  One approach can be to place the risk of change in law with the contractor up to a threshold value beyond which the client compensates the effect of increase in cost, decrease in return for additional financial burden imposed.

- Delays in land acquisition. This delay can have significant impact on the execution of rehabilitation works. This risk may have different implication for contractor and employer depending on timing of civil works and selected payment model.  The consultant may propose methods to mitigate this risk.

- Road safety and climate resilient risks: These have traditionally been analyzed as interventions and not been subjected to market forces. By identifying them and assigning them to the responsible contract party, these risks can be addressed during contract preparation and costing applied to risks that lend themselves to assessment. These risks should be analyzed at all contract phases i.e. design, construction, operation and maintenance.

Other risks can be:

- New roadside development

- Capital/improvement works being undertaken by others

- Work undertaken by Utility operators within the Road Right of Way.

- Environmental Compliance

- Influx of migrant labor to rural communities

- Access control or lack thereof

- Any other risks directly or indirectly related to the project area.

The Consultant shall follow a comprehensive approach to identify such risks and propose appropriate risk-mitigation plan.

## 3.3	Phase 1-2:  Review of the Existing Engineering Design

### Task 2-1:  Review the Adequacy of Existing Design Documents and Information

Design Studies done in the past will be made available to the Consultant for reference.  The Concept design reports to be prepared by the consultant will consist of, but not limited to:

- Road surveys

- Roughness surveys

- Traffic counts and axle load survey

- Road inventory and visual pavement condition

- Road deflection by FWD

- Bridge and drainage structure and hydraulic condition analysis

- Preliminary/conceptual design for the rehabilitation works

- Environmental and Social screening report

- Road safety report

- Identify accident black spots, high risk locations and suggest remedial measures

- Economic and financial analysis using the concept of life cycle cost

- Geotechnical data including availability of road building materials

The Consultant shall review the available information in terms of its adequacy for (i) design and specification of civil works and (ii) the implementation and management of a long term OPBRC contract. At the end of this task, the Consultant shall submit a technical report on each of these issues outlining the findings and recommendation for consideration by GOM. These recommendations shall identify all data omissions and a plan for additional data to be collected within the overall time available under this contract.

Based on the existing available documents, the Consultant shall carry out a desk study to familiarise himself to the full particulars of the available design and carry out such field investigations necessary to ensure an update of technically and economically feasible maintenance, rehabilitation and re-construction designs for pavements, drainage, structures, and ancillary elements. This phase will include verification regarding the sufficiency of the proposed rehabilitation design and strategy with rationale on the updated and/or validation of relevant design factors such as updated conditions on traffic demands, geometry and drainage, hydrological and hydraulic conditions, materials availability, maintenance or improvement of the drainage system, the ancillary roadworks, the maintenance, rehabilitation or reconstruction of bridges, among others.

The Consultant shall also consider subdivision and packaging of the road (to fit into the available financing), create a contiguous and consistent road network with proposals to add/subtract from the defined road links, the capacity of the local industry and responsiveness of international contracting industry.

Specifically, the Consultant in this phase shall review the existing engineering designs, field visits and consultations, among others, including the following aspects:

- Generic and specific technical studies (traffic volumes, traffic model for predicted traffic within the pavement design period of 20 years);

- Field investigations, specifically the pavement investigations;

- Accuracy of the topographical survey and the triangulation beacons established;

- Sufficiency and accuracy of the horizontal and vertical alignment proposed in view of the revised design standards adopted by ANE;

- Accuracy of the materials investigations, available quantities and the adequacy of the strategy proposed for the contractor to identify and confirm the suitability of the sources of materials through site and laboratory testing during the execution of the civil works contract;

- Adequacy of the pavement design with respect to its strength, use of available materials, economy factors and revised traffic volume, design life, and loading;

- Adequacy of the measures taken to ensure safety such as the road cross section, adequate signing, road markings, pedestrian crossings, parking lanes, bus bays and footways;

- Adequacy of plans for the protection and relocation of utility services and request updated information from the public utility companies concerning any changes since engineering design documents were prepared;

- E&S constraints identified in the E&S documents prepared for the project, namely in the baseline characterization included in the ESMF and ESIA.

- Make amendments to earlier designs, where appropriate, in order to update the engineering decisions in line with the requirements for the new concept design;

- The evaluation of the road alignment for a 20-year analysis period;

- Recommend the appropriate rehabilitation design option for the road and all related structures and services, based upon a clear technical, economic, environmental, and social rationale, and do a life cycle cost comparison among the two identified options.  The consultant shall present at least two (2) pavement rehabilitation design solutions based on the type of road building materials encountered within the project area;

- The evaluation of the condition and adequacy of the drainage structures, including inter alia, the evaluation of the adequacy of the waterway openings of the existing bridges in view of updated hydrological analysis and hydraulic discharge capacity considering the impact of climate change and any land use changes in the catchments.  It should be noted that the Client has recently undertaken an extensive survey of all bridges on the N1 and the report of this work will be made available to the consultant;

- Assessment of a structural capacity of existing bridges in terms of the traffic and environmental conditions forecast for the 20-year structural design period;

- To propose maintenance activities to bridges. The maintenance activities will be aimed at repairing or protecting concrete elements (e.g. cracking and spalling), repairing or protecting steel or concrete balustrades, evaluation and repairing expansion joints as necessary, replacing bridge bearings as required, improving the erosion and scour protection, and other activities as necessary;

- The design of the upgrading of the road alignment and widening of the carriageway width and structures where required;

- Review the traffic survey data and supplementary services;

- Undertake classified traffic counts. The traffic counts are for twelve (12) consecutive days and on some of the days are for a full 24 hours, with at least two 24-hours counts on a weekday and two during a weekend. On the other days 16-hour counts should be sufficient. These should be extrapolated to 24-hour values in the same proportion as the 16-hour/24-hour split on those days when full 24-hour counts have been undertaken. A total of 6 counting stations, strategically located, should be considered.

Carry out axle load survey which should include collection of relevant data to determine current overloading in relation to axle load limits and gross vehicle weight limits. Relevant axle load data over the last five years would also be assembled to determine the effectiveness of weighbridges in controlling overloaded vehicles. The consultant will evaluate the issue of loading in some detail in order to understand whether actual axle loading matches with what is to be considered during detailed design.

- Check that the geometric designs, for sections of the road which are to be improved, satisfy the requirements by altering the alignment or increasing the road width as required. It is not expected that the existing alignment will be changed other than for road safety requirements, minor changes already identified in the existing engineering designs or those required to incorporate the surfaced shoulders, revised carriageway cross section and possible heightening or lowering of finished road levels for climate resilience purposes.

- Investigation on the suitability of existing pavement and subgrade materials to be re-utilised as well as the identification of suitable concrete and road building material sources such as sand for concrete and other pavement materials incorporation, cement, source of aggregates, water quality, etc.

- Identify high risk crash locations based on iRAP star ratings (carried out by iRAP jointly with ANE), crash data collection and local consultations with key-stakeholders (traffic police, transporters, community leaders) to feed into the RSA (carried out by the Consultant) and recommend road safety engineering measures as part of Concept Design.

- In parallel to the iRAP star rating for the N1 corridor, ANE has also prepared star rating for schools located near the N1 road corridor. On the basis of this star rating for schools, important road safety engineering measures (pedestrian crossings, pedestrian walkways) have been identified which need to be incorporated in the Concept Design package prepared by the Consultant.

### Task 2-2:  Carry out additional technical surveys and site investigations

A provisional sum (PS) of US$ 0.20 million shall be kept to collect the additional data (as required) for OPBRC. This amount can be used only with the specific approval from the Client. After the approval of technical report mentioned in Task 2.1 , the Consultant shall proceed to collect the additional data required. The actual amount payable shall be based upon the agreed additional data to be gathered and unit prices contained in the financial proposal.

On the completion of this task the Consultants shall provide a report on the data and its implications for the management of the contract. The data shall be stored in a database, which can be distributed to the Contractors, and reported in a manner suitable for inclusion in the contract documents. The data may also be required to be handed over to other Consultants to be linked to GIS maps.  Throughout the survey and engineering design process the consultant should be attentive to the potential for the contractor’s detailed design to adopt lower standards than might be ideal from the client perspective, the key risk being the pavement design. To mitigate this risk, a minimum pavement design is envisaged in the bidding documents.

The early application by the Client for permits related to borrow pits and quarries could significantly reduce the delays in obtaining the appropriate authorizations.  The consultant should assist the Client in the identification of materials sources and the initiation of the application process at the earliest possible point.

### Task 2-3:  Climate Vulnerability Risk Assessment (CVRA)

The purpose of a CVRA is to identify and evaluate the effects of climate change on the N1 road sections to identify the most vulnerable sections and recommend climate adaptation measures to increase its resilience. The CVRA makes use of geo-spatial data, in which data layers of Exposure, Vulnerability and Hazard are overlaid in a GIS-based analysis to identify climate related hotspots and prioritize adaptation measures, which will then be included in the concept design. The CVRA approach combines a quantitative and qualitative assessment using primary and secondary data sources. Important sources of primary data are stakeholder consultations to identify vulnerable road sections that, historically, have been exposed to extreme weather events. But equally, the CVRA should consider exposure to future (projected) climate hazards such as increased risk to river channels from flash flooding due to changes in extreme rainfall intensities or due to changes in land-use such as extensive deforestation, farming, residential or industrial developments. As part of its technical approach and methodology, the Consultant should propose in detail how it plans to carry out the CVRA. Several flood events have occurred in the recent years, the Consultant shall analyze the damage to flood affected areas related to these events and include the need for specific climate resilient solutions at these locations in the design requirements. Information regarding these events will be collected from the ANE Headquarters and Provincial Delegations.

The consultant shall consider the issue of flooding in the update of the vertical alignment and propose updates to the drainage system and protection against erosion in order to resolve the occurrence of damage and the interruption to traffic caused during flooding events.

### Task 2-4:  Road Safety Assessment/Appraisal

The consultant shall carry out a Road Safety assessment/appraisal on the existing road for identification of existing accident black spots and high risk locations along the corridors. The Consultant should identify and recruit an accredited road safety auditor for this purpose.

The client expects to undertake a separate road safety audit at the time of detailed design by the contractor.

### Task 2-5:  Identification of E&S Requirements relevant for the Development of the Conceptual Design

During the preparation of the SRSEIP, several E&S issues relevant to the development of the Conceptual Designs were identified, and measures were proposed to avoid or minimize the anticipated adverse impacts, which need to be integrated into the design development. For instance, regarding involuntary resettlement, the RPF flags several social issues related to the Project Affected People (PAP) and establishes the width of the Corridor of Impact (CoI), which will now need to be carefully assessed during the Conceptual design stage. To minimize physical and economic displacement, the RPF recommends that adjustments in road alignment in populated areas should be avoided as much as possible, as these may trigger significant compensation measures.

Aiming to identify all E&S issues/constraints and mitigation measures relevant to the development of the Conceptual design, the Consultant will need to engage the E&S consultant responsible for the preparation of the E&S instruments mentioned above (who will also be responsible for undertaking the project’s ESIA/ESMP and RAP).

This engagement with the E&S consultant shall begin in the early stage of the services through a joint workshop held between ANE and both consultancy teams aiming to present and explain the E&S documents prepared so far and their main outcomes in terms of project design requirements and constraints.

The engagement between both consultancy teams shall be continuous throughout the concurrent development of the Conceptual design and the preparation of the ESIA/ESMP and RAP, ensuring the reciprocity of information between them. Under its technical proposal, the consultant shall describe the methodological approach and workplan proposed to ensure such close collaboration.

## 3.4	Phase 1-3:  Preparation of Conceptual Design and Bidding documents

### Task 3-1: Definition of service levels of the road.

The Consultants, in consultation with ANE, shall define the appropriate service levels/maintenance standards for the OPBRCs. This exercise will be based on:

- Existing standards of ANE for primary roads and corridors

- Past Feasibility study reports and Detailed Design Reports,

- Technical surveys and investigations carried out by the Consultant including road and bridge conditions,

- Information collected during field visits to the road,

- Analysis of typical road use and road user needs for the road, including formal consultations and informal discussions with road users and local communities,

- Establishing a link between road user needs and the required service level class, and

- Affordability of service levels and the availability of realistic and sustainable funding levels following discussion with the Road Fund (FE).

Monitoring and Evaluation (M&E) Framework. The Consultants will also conduct necessary baseline survey which covers inter alia, road standard and condition, trip time, traffic volume, transportation costs, road safety characteristics and prepare an M & E  program to measure the impacts of the improved road network on the development of the intervention areas.

### Task 3-2:  Conceptual Designs, Financial Model/payment Schedule and Confidential Price Estimate for Civil Works Contract (Package).

The Consultants shall undertake an analysis to estimate the long-term investment requirements, using relationships such as those contained in the HDM IV model or similar. The Consultants shall ensure that the modeling relationships are properly calibrated, and used to suit the objectives of the contract. The Consultant’s shall finalize in details the required initial capital investment, the required service/ maintenance standards and the output and performance criteria. The conceptual design will include details of structures, cross sections; longitudinal and horizontal alignment; pavement details; drainage details; details of topographical survey polygon etc. as provided in the existing detailed design (if any) and those updated during the review.

Climate change impact and adaptation should be considered in the preparation of the conceptual design. Hydraulic discharge capacity of structures should be calculated using historical extreme rainfall analysis (baseline) that corresponds to the chosen design period of the structure, and the projected uplift/decrease (% change) as a result of climate change based on:

- Greenhouse gas emission scenario: Representative Concentration Pathways (RCP) 8.5

- Source of data: Intergovernmental Panel on Climate Change (IPCC), Global Climate Models (GCM), extreme value data set, regionally downscaled

- Confidence level: 90% percentile values of projected extreme rainfall (max. 24h and max. 5-day rainfall)

Alternately, the Consultant may consider other adaptation measures such as submersible sections of the road to allow flood water to flow over as sheet flow during high flood events. A key factor is to balance the cost of hardening that may still fail vs. cost of temporary disruptions.

The conceptual design and book of drawings will include details of structures, cross sections (typical at scale 1:50), longitudinal and horizontal alignment at 1: 2,000 scale, pavement design and its composition with material classification, drainage details, details of topographical survey polygon, GIS, etc.), standard drawings for structures, etc. The Consultants shall also carry out cost /benefit analysis using the concept of life cycle cost (inclusive of sensitivity analysis).

The outcome of the concept design stage should be a set of design documents that allow bidders to compete on equal footing i.e. bid proposals are comparable in terms of minimum required: design life, finished road level, standard cross section, location and minimum opening of drainage structures, whilst allowing sufficient room for bidders to propose innovative and cost-effective engineering solutions for pavement design, use of local materials, recycling technology, surfacing technology and structural design. However, bidders (contractors) under OPBRC are free to propose additional investments (e.g., embankment levels, more drainage structures) if according to their assessment this may result in cost savings during the maintenance (performance period).

Road Safety standards. The Consultants should follow international best practices while carrying out the Conceptual Design. Based on the results of the Road Safety Assessment/Appraisal, the Consultant should also include proposed improvements to the existing accident high-risk locations along the corridors in the proposed conceptual design. The Consultants are requested to propose measures in the action plan regarding techniques intended to safeguard the future Right of Way (ROW) of the road.  If approved, these measures may be included in the requirements of the works contract.

The Consultant should collect data as minimum requirement to conduct a road safety analysis under the study. This data should be collected for the Baseline (existing) Scenario and subsequently for the Project Scenario. However, the analysis of the Baseline scenario and various project alternatives should inform the design of the Project (concept and detailed designs)

•	General characteristics:

A.	Segment length in Km (different homogeneous segments may need to be identified, based on the road characteristics i.e., area type, such as urban/inter-urban/rural and road users present)

B.	Area type

C.	GDP per capita

D.	Growth rate GDP per capita (%)

•	Crash Data:

A.	Baseline Fatalities

i.	Annual fatalities (according to road segments if applicable)

ii.	Serious Injury/Fatality Ratio

B.	Baseline annual fatalities breakdown (percentage or number)

i.	Vehicle Occupants

ii.	Motorcyclists

iii.	Pedestrians

iv.	Bicyclist

Based on the capabilities of contractors identified under the Task 1-4, the Consultants will confirm the adequacy of the size of the selected road sections for OPBRC contract, in terms of the number of road-km included in the contracts. Any variation in length will not influence the overall requirements and associated compensation of the Consultant under this assignment.

Confidential Price estimate The Consultants shall prepare a confidential price estimate for the OPBRC civil works contract(s) to be tendered for the road sections under consideration. This shall include price estimates for (i) maintenance services during rehabilitation phase, (ii) rehabilitation works iii) improvement works, if required, (iv) emergency works, and (v) cost to always maintain the road at the desired quality during the period of the civil works contract and a potential ten-year maintenance period. The purpose of the confidential price estimate is to obtain a benchmark price for civil works package/s (contract/s), against which actual bids can later be compared. The basis for the conceptual design may include a simplified BOQ in order to reach the cost estimate for the adopted option, based on the unit cost analysis, broken down to taxes, levies and other costs and then be compared with the project cost for similar road interventions done in the sub-region in general, and in Mozambique in particular, in the period of last 10 years.

The cost estimates will provide for the planned activities within the right-of-way for the roads in the period of about 10 years (the approximate period needs to be justified). Cost of all environmental and social impacts mitigation measures including GBV/SEA/SH response and mitigation measures, HIV / AIDS interventions included in the project’s ESMF, ESIA/ESMP, LMP, SEP will also be added. The conceptual design will include all required technical specifications, standards, management measures, etc. for the planned activities in the design, construction and maintenance phases of the project.

The financial model and the associated payment model (cost recovery model) in at least three alternatives as mentioned in Task 1-3 shall be confirmed so as to define the most suitable and optimized method of payment schedule to the contractor, as well as to define “the best value for money” the client will pay to the contractor.

The cost estimate will be based on conceptual designs and road works specifications for each road, which will include the typical cross sections and other typical geometric design parameters and be based on basic field surveys (traffic counts and forecasting, topographical and soils/materials).  The Bidding Documents will explain the financial and payment models which will be mandatory and will be one of the conditions of the civil works OPBRC.

Specifically, the Consultant for this assignment, based on his completed review, will update the previous information in the following areas:

- Generic and specific technical studies (traffic volumes, traffic model for predicted traffic within the pavement design period of 20 years;

- Basic Field investigations, specifically the pavement investigations (using non-destructive methods such as FWD);

- Definition of LOS, which must be specified for the period during-construction and after-construction, as well as the payment structure;

- Specific technical studies and the preparation of bidding documents for Output- and Performance-based Road Contracts (OPBRC), and;

- Support to the procurement department of the Contracting Entity, for procurement activities related to the civil works contracts.

### Task 3-3:  Integration of E&S Requirements in Development of the Conceptual Design

To ensure that all relevant E&S issues and applicable mitigation measures will be adequately integrated in the development of the Conceptual design, observing all requirements stated in the national E&S regulatory framework and World Bank ESF, it is fundamental that the consultant works concurrently and in close collaboration with the consultant hired to prepare the project’s ESIA/ ESMP and RAP (who was also responsible for the E&S instruments developed prior to the Project’s Board approval). This work approach aims to maximize the interactions between the teams involved in both assignments, thus ensuring the environmental and social soundness of the proposed project solutions/alternatives, as well as full reciprocity of information between the Conceptual Designs and Bidding Documents and the ESIA/ESMP and RAP.

To this aim, the methodological approach and work plan proposed by the Consultant should specifically identify key inputs required of the E&S consultant at different stages of the work. The scope of services includes, but not be limited to, the following main tasks:

- Conduct regular meetings with the E&S consultant hired to (i) show how the E&S issues/constraints and mitigation measures identified in the ESIA/ESMP and RAP are reflected in the conceptual design; and (ii) provide updated information on the conceptual design to the E&S Consultant, so that the latter can better assess the project’s anticipated E&S risks and impacts and detail the required mitigation measures;

- Verify if all mitigation measures defined in the final versions of the ESIA/ESMP and RAP are adequately taken into consideration in the conceptual design and priced in the cost estimate;

- Some rural sections of the road pass through undeveloped areas of terrain which provide habitat for a rich biodiversity of wildlife. In particular, the Inchope – Gorongosa and Gorongosa – Caia sections of the N1 which represent the western and northern limits of a Key Biodiversity Area (KBA) Gorongosa National Park and Marromeu Complex, while also crossing four different Coutadas (hunting concessions).  The Consultant shall collaborate with the biodiversity specialists of the E&S Consultant in developing appropriate measures aimed at reducing the risks that arise from this conflict, both to wildlife crossing the road and from a road safety perspective.

### Task 3-4:  Estimate and Pricing for Emergency Works

In coordination with ANE, the Consultant shall determine and justify whether unit prices for Emergency works should be subject to bidding or should rather be fixed in advance based on existing market rates. If the latter option is elected, he shall identify the prevailing market rates based on recent contracts or those under execution. He shall further determine the provisional sum for Emergency works for the contracts. Also, he shall identify the work units applicable for emergency works for which unit prices are to be established.

The Consultant shall include the provisional sum in the bid document to cover Emergency Works.  The consultant shall provide a detailed breakdown of the anticipated quantities, materials, or items that the provisional sum covers, along with any associated unit rates or pricing information. He shall also establish a clear procedure for approving and executing provisional sum works during the project, including any necessary documentation or reporting requirements

### Task 3-5:  Preparation of Contract Documentation (Draft and Final Conceptual Design Reports and Draft and Final Bidding Documents).

Definition of standard clauses for all contracts: The Consultant may consult the Sample Specification for OPBRC, annex to the latest World Bank Standard Procurement Documents (SPD) , Request for Bids, Output and Performance-Based Road Contracts, February 2021.

Following World Bank ESF requirements, also reflected in the SPD for OPBRC above, the OPBRC format needs to integrate the mitigation measures and monitoring and reporting procedures resulting from MPA SRSEI E&S, such as: the Environmental and Social Management Framework (ESMF), the Environmental and Social Impact Assessment study (ESIA)/Environmental and Social Management Plan (ESMP), the Resettlement Policy Framework (RPF), the Resettlement Action Plan (RAP), the Stakeholder Engagement Plan (SEP), the Labour Management Procedure (LMP), the Social Assessment (SA) and the Gender-based Violence (GBV) risk assessment [including Sexual Exploitation and Abuse (SEA) and Sexual Harassment (SH)].

Generic Environmental and Social Clauses included in ESMF Annex 9 must be taken into consideration, detailed and attached to the OPBRC.

The latest versions of the OPBRC SPD have been prepared for projects which have been assessed as having a high risk for Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment (SH).

The Consultant shall Include compliance of E&S measures in the payment structure (assigning  appropriate weightage) and propose key service levels to be monitored and incorporated in the payment of the contractor. For example, Lost Time Injury, number of trainings for labor force and public can be tracked be part of payment mechanism.

Preparation of Bidding Documents: The Consultant will complete the bidding documents for the OPBRC contract, including reports, plans, maps, drawings, sketches, specifications, bills of quantities etc. by first submitting the draft report and bidding documents to the Client for review and, after receipt of the Client’s comments, finalizing the same for advertisement.

The Consultants shall propose a framework for a project document control system to be used for monitoring the project during implementation. This system will be used to maintain all engineering reports and records to adequately document the programs and performance of the work. The system shall be designed and developed consistent with standard formats that can be used to document decisions, minutes of meetings and any other communications, which might direct actions on the project. Document control shall involve sequential logging of incoming and outgoing correspondences on a computerized system to establish a chain trail of correspondences for custody. The control function shall be designed to ensure distribution to all concerned.

The Consultant’s proposal should be developed to ensure maximum local participation through skills transfer, capacity building or any other strategy that will promote the development of the domestic construction industry.

The submission and acceptance of the complete Final Conceptual Design Report for the section of road and Final Bidding Documents will be seen as the final output for this task. The Final Conceptual Design Report for the section of road and the Final Bidding Documents will be prepared and issued for comments to the Client and the World Bank first in Draft Format so as to receive the necessary comments/observations/ suggestions, which will thereafter be incorporated in the Final Documents. If required, the Consultants will also prepare Pre- Qualification Documents, in accordance to the World Bank procedures. The Draft and Final Reports will include an Executive Summary, as well as all information/options/analysis and the preferred alternative for the selected road, that have been collected and analyzed during the process of the implementation of this assignment.

## 3.6	Phase 2:  Support to the procurement process  until the award of contract;

The Consultant will assist the Client in preparation of a pre-Bid conference, carry out the pre-bid conference and site visit and will assist in preparation of Bid Evaluation Report- BER.

### Task 4-1:  Prequalification of Contractors

N/A

### Task 4-2:  Pre-bid workshops

The Consultants shall support ANE in the organization and execution of one-day pre-bid workshop.

The purpose of the workshop is to go through the various elements of the OPBRC Contracts, in order to make sure that bidders fully understand the nature of the contract and its requirements, and are thus able to present reasonable and responsive bids. Notes covering salient points of OPBRC Contracts shall be prepared and distributed among the contractors during the workshop.  In particular, the elements of risk and responsibility should be clarified in detail for the attendees.

OPBRC Environmental and social requirements must also be clarified to tenderers.

### Task 4-3:  Tender Process and Evaluation of Tenders

Given the complex nature of the work, significant degree of risk transfer to the contractor and effort required to tender for such work, it is expected that the tender period shall be at least three months. Tendering workshops shall be held with the bidders to ensure that they are fully aware of the nature of the work and the risks involved.

During the tender process, the Consultants shall support ANE as necessary for such matter as:

- providing information to issue as necessary,

- any addenda varying or clarifying the scope of the contract

- technical assistance with the necessary bid evaluation procedures including E&S criteria and,

- pre-contract discussions with the preferred bidder.

- Preparation of Contract Document and Signing.

If the Consultant has any reservations as to the appropriateness of the bidding and selection process, he shall be obliged to immediately inform ANE in writing.

He shall further support ANE in finalizing the contracts until both parties reach agreement.

# 4.	DURATION OF THE ASSIGNMENT AND REQUIRED INPUT

## 4.1	Duration and Input for Phases 1 and 2

Phase 1 and 2 will give a combined duration of 12 calendar months from the date of commencement. The first 6 months, the consultant will concentrate and complete the technical studies, preparation of the conceptual design, cost estimates, contract and bidding documents. The last 6 months are for the procurement support.

| Activities | Duration |
| --- | --- |
| Phase 1-1: Development of Contracting Strategy | 6months |
| Phase 1-2: Review of the Existing Engineering Design, Conduct Technical Surveys, conduct a Climate Vulnerability Risk Assessment (CVRA), Collection of Additional Data and Road Safety Assessment/Appraisal; |  |
| Phase 1-3: Conceptual Designs, Financial Model/Payment Schedule and Confidential Price Estimate for Civil Works Contracts and Integration of Environmental and Social (E&S) Requirements in the Development of the Conceptual Designs and bidding documents |  |
| Phase 2: Support to the Procurement Process until the award of contract | 6months |
| TOTAL | 12 months |

As an integral part of the Services, the Consultant shall establish a Quality Assurance System (QAS). The system will be based on a quality management approach and will apply to both the services of the Consultant and Contractor for the works’ execution.

The procedures as prepared by the Consultant will cover all requisite planning, controlling and documentation processes:

Under planning, the objectives, goals, authority, and responsibility relationships of each activity are to be defined and understood;

Under controlling, measures will be instituted to ensure the meeting of goals and objectives and the taking of corrective action to avert problems.

Progress reporting should report on how well the quality management system is performing to satisfy the Employer’s needs and what kind of changes, if any, are necessary.

In addition, the following budgetary provisional sums (PS) will be available for this assignment (Consultant should indicate these PS in his proposal):

- Collection of additional data US$ 200,000 (Task 2.2)

- Training and 2 workshops, US$ 30,000 (provisional sum)

# 5.	REPORTS TO BE SUBMITTED

## 5.1	Reports Related to Phases 1 and 2 of the Assignment

| Report | Content | Due Date | Review Period | No. of Copies |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Hard Copy | CD |
| Inception Report | Should include introduction of all team members and tasks assigned to them and how each task is proposed to be carried out, the project quality assurance plan, technical approach, the methodology, the equipment, and the software(s) which the consultant proposes to use and proposal(s) to train the counterpart personnel. Identify main E&S issues/constraints and mitigation measures identified in the E&S instruments develop during the project’s preparation and describe the proposed methodological approach and workplan to ensure close collaboration with the E&S consultant throughout the development of the Conceptual design. | 1 month from date of start | 7 days | 3 | 3 |
| Interim Report 1 | Task 1-1: Definition of service levels, | 3 months from date of start | 15 days | 3 | 3 |
|  | Task 1-4: Review of Contracting Capacity: Report on existing state of the contracting industry to deliver OPBRC Contracts. Recommendations regarding actions required for improving capability and capacity of contracting industry |  |  |  |  |
|  | Task 1-5: Development of contract format |  |  |  |  |
|  | Task 2-1: Report on review of adequacy of existing document |  |  |  |  |
|  | Task 2-2: Report on collection of additional data |  |  |  |  |
|  | Task 2-3: Report on CVRA Task 2-4:Report on Road Safety Assessment/ Apraisal |  |  |  |  |
| Interim Report 2 | Task 1-6: Industry Consultation Workshop: Final OPBRC contract format after discussion with ANE and industry workshop | 4.5 months from date of start | 15 days | 3 | 3 |
|  | Task 1-7: Development of approach to risks: Report on Risk Allocation |  |  |  |  |
|  | Task 2-2: Carry out additional technical surveys: Compiled data report (fit to be handed over to contractor). This involves all physical and foreseen data, field investigations testing/results /interpretations, topographical surveys, soil/material reports and maps, traffic current and predicted model, etc.). Task 2-5: E&S Requirements for Conceptual Design: Update |  |  |  |  |
|  | Task 3-1: Service Levels |  |  |  |  |
|  | Task 3-2: Conceptual Designs: Report on long term pavement strengthening and resurfacing strategies; Financial Model Report and recommendation; Task 3-3: Integration of E&S Requirements: Checklist/report with types of E&S impacts and respective corrective actions to avoid and/or mitigate them in the Conceptual design based on inputs provided by the E&S Consultant. |  |  |  |  |
| Draft Final Reports | Task 1-2: Cost/ Benefit Analysis | 5.5 months from date of start | 15 days | 3 | 3 |
|  | Task 1-3 Financial and Payment Models |  |  |  |  |
|  | Task 3-2 Conceptual Design meeting technical, environmental and social framework; Confidential price estimate for the civil works; Financial Model and Payment Schedule model report and recommendation; |  |  |  |  |
|  | Task 3-5: Draft Contract Documents (Draft Final Conceptual Design Report and Draft Bidding Documents. Draft Final Conceptual design Report will include Executive Summary and ALL information/studies/analysis/solutions and recommendations collected and developed along the course of the Assignment. |  |  |  |  |
|  | Task 4-2: Brief notes covering salient points of bidding documents to be distributed among the contractors during the pre-bid workshop. |  |  |  |  |
| Final Conceptual Design Reports and Final Bidding Documents | Task 3-5: The Final Report will include all elements and Tasks included in the TOR and the possible modifications, if required, based on the comments on the Draft Final Reports/Bidding Documents and the comments and experiences obtained during the pre-bid workshop. Task 3-3: Final Checklist/report with types of E&S impacts and respective corrective actions to avoid and/or mitigate them in the Conceptual design. And Checklist/report with types of E&S instruments and procedures integrated in Bidding Documents. The Final Reports shall incorporate the modifications approved by review committee and the World Bank. | 6 months from date of start | 15 days | 3 | 1 |
| Bid Evaluation Report | § Bid Evaluation Report and Workshop/s Report/s as well as § Training Plan § Report upon conclusion of each workshop | 12 months from the date of start | 15 days | 3 | 1 |

## 6.	TEAM COMPOSITION

## 6.1	Team Composition for Phase 1 and 2

It is the Consultant’s responsibility to provide the required inputs of Key Professionals for the assignment; provide necessary logistic arrangements to render these services efficiently and diligently. It’s estimated that 56 person/months will be required to implement this assignment timely and orderly. When proposing the team members, the Consultants should make sure that the proposed staff are actually available and aware of the intensity of the required travel. Any change in key personnel shall be permitted only under exceptional circumstances and if evidenced as equal or better than the initially approved candidate.

## 6.1	Staff Qualifications Phase 1 and 2

The Consultants shall submit names, Curriculum Vitae (CVs) and copies of qualifications for all these key professional staff. The copies of qualifications shall be in English or accompanied by translations in English where the original qualifications are not in English. All the key staff are required to be proficient in English. The evaluation will be based on the following key professional staff.

| Indicative Time inputs to MPA Concept Design and Procurement Process | MPA Phase 1 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Package 1 (154 km) |  | Package 2 (178 km) |  | Package 3 (176 km) |  |
| Key Professional Staff | Inchope - Gorongosa (70km) | Gorongosa - Caia (0-84km) | Gorongosa - Caia (84-168km) | Metoro - Pemba (94km) | Chimuara - Nicoadala (0-88km) | Chimuara - Nicoadala (88-176km) |
| Detailed Design/Year | 2016 | 2016 | 2016 | Not Available | 2010 | 2010 |
| Maintenance Period (Years) | 10 | 10 | 10 | 10 | 10 | 10 |
| Design Period (Months) | 6 | 6 | 6 | 6 | 6 | 6 |
| Procurement Period (Months) | 6 | 6 | 6 | 6 | 6 | 6 |
| DESIGN |  |  |  |  |  |  |
| Team Leader (Senior Highway Engineer) | 5 | 5 | 5 | 5 | 5 | 5 |
| Pavement Management Specialist | 3 | 3 | 3 | 5 | 3 | 3 |
| Geotechnical/ Materials Engineer | 2.5 | 2.5 | 2.5 | 4 | 2.5 | 2.5 |
| Road Safety Specialist / Traffic Engineer | 3 |  | 3 |  | 3 |  |
| Bridge Engineer/ Structural Engineer | 3 | 3 | 3 | 4 | 3 | 3 |
| Accredited Road Safety Auditor | 2 |  | 3.5 |  | 2 |  |
| Hydrologist/ Climate Change Adaptation Specialist | 2.5 | 2.5 | 2.5 | 3 | 2.5 | 2.5 |
| Procurement/ Contract Specialist | 1.5 |  | 2 |  | 1.5 |  |
| Transport Economist/ Financial Model Analyst | 2.5 |  | 3 |  | 2.5 |  |
| Legal Advisor | 2 |  | 2.5 |  | 2 |  |
| Environmental, Health and Safety Specialist | 2 |  | 2.5 |  | 2 |  |
| Social Expert, GBV, SEA, SH Specialist | 2 |  | 2.5 |  | 2 |  |
| TOTAL Person – Month | 47 |  | 56 |  | 47 |  |

Team Leader (Senior Highway Engineer): He should have BSc degree in Civil/Highway Engineering with minimum of 20 years professional experience in the road sector of which 10 years in developing countries. Minimum of 2 similar projects successfully completed in the last 10 years in a similar position and role, covering: highway/ road design and maintenance in tropical countries and experience in the use of OPBRC contracting modalities. Previous proven involvement, in leading role for OPBRC/DBT /PPP type of projects is required. Fluency in both written and spoken English language.

Pavement Management Specialist: The candidate should have BSc degree in Civil engineering with minimum of 15 years of experience in Pavement management systems of which 7 years in developing countries. Minimum of 2 similar projects successfully completed in the last 10 years in a similar position and role, covering pavement management systems. Fluency in both written and spoken English language.  Note: Significant experience (4 years or more) of sealed road construction, routine and periodic maintenance should be encountered in this candidate or in the Team Leader.

Geotechnical/ Materials Engineer: The candidate must have BSc degree in Civil engineering, Geology or related field with minimum of 15 years professional experience in the pavement engineering and materials of which 7 years in developing countries. Minimum of 2 similar projects successfully completed in the last 10 years in a similar position and role, covering: pavement design, materials and sub-grade investigations. Fluency in both written and spoken English language.

Road Safety Specialist / Traffic Engineer: The candidate will have Bsc degree in civil engineering and minimum 10 years of working experience of which minimum 7 years’ experience in conducting road safety assessments (including stakeholder consultations, crash data collection) and traffic engineering as part of highway design projects. Fluency in both written and spoken English language and ability to communicate are essential.

Bridge Engineer/ Structural Engineer: BSc. in Civil Engineering/ Structural Engineering. Minimum of 15 years professional experience in the design of bridges and other drainage structures of which 7 years in developing countries. Minimum of 2 similar projects successfully completed in the last 10 years in a similar position and role, covering: bridge design, geotechnical investigations and CAD related work. Fluency in both written and spoken English language.

Accredited Road Safety Auditor: BSc. in Civil Engineering. Minimum of 15 years professional experience in the conducting road safety audits at various stages of the project cycle of which at least 7 years in developing countries. Minimum of 5 years accumulated experience in the last 10 years in a similar position and role, covering: road safety audits (all 5 common stages) in major highways, design road safety improvement schemes. Fluency in both written and spoken English language.

Hydrologist/ Climate Change Adaptation Specialist: Minimum BSc degree in Civil Engineering, Hydrology, Water Management, Flood Management. Minimum of 15 years professional experience in the hydrological analysis and hydraulic design of drainage structures of which 7 years in developing countries. Minimum of 2 similar projects successfully completed in the last 10 years in a similar position and role, covering: statistical analysis of historic rainfall, conducting climate vulnerability and risk analysis, determination of uplift factors for extreme rainfall, hydraulic design of road drainage and structures including climate adaptation measures, using Standard Engineering Software Packages (HEC-RAS or similar). Fluency in both written and spoken English language.

Procurement/Contract Specialist: Minimum BSc degree in Engineering or an equivalent relevant qualification. Minimum of 15 years professional experience in the procurement of works, services and goods. Minimum of 4 years accumulated experience in the last 10 years in a similar position and role, covering: DBMO contracting methodologies (preferable OPBRC), FIDIC conditions of contract, preparation of civil works bid documents using the World Bank Standard Biding Documents, bid evaluation including analysis of unit rates. Fluency in both written and spoken English language.

Legal Advisor: The candidate must have a minimum of 15 years’ experience on legal drafting of legislations, regulations and contracts connected to the transport sector development. A registered attorney, with a minimum of a LLB academic degree (Bachelor of Laws) or equivalent, and a minimum of 10 years post registration experience in carrying out cases related to contract law for civil engineering works. Knowledge of appropriate Mozambican laws is an advantage. Fluency in both written and spoken English language.

Transport Economist/ Financial Model Analyst: The candidate must have a minimum of 15 years’ experience in financial management applied in major infrastructure projects. Minimum of 4 years accumulated experience in the last 10 years in a similar position and role, covering: OPBRC financial modeling and preparation of maintenance payment schedule options. A minimum equivalent education comparable to BSc. in Engineering or Business Management. Fluency in both written and spoken English language.

Environmental, Health and Safety Specialist: The candidate must have a minimum BSc degree in Environmental Science or an equivalent relevant qualification with some certification on health and safety matters. Minimum of 10 years professional experience in environmental safeguards preparation and management of which minimum 5 years in developing countries. Experience in Southern African countries will be an added advantage. Minimum of 5 years accumulated experience in the last 10 years in a similar position and role.  Phase 1 and 2 will require strong experience covering the preparation of Environmental documentation for road projects in developing countries using World Bank environmental safeguard policies.

Social Expert, GBV, SEA, SH Specialist: The candidate must have a minimum BSc degree in Social Science, Public Health, Intercultural Communication or an equivalent relevant qualification. A minimum of 10 years professional experience in social safeguards document preparation and management of which minimum 5 years should be in developing countries. Experience in Southern African countries will be an added advantage. A minimum of 5 years accumulated experience in the last 10 years in a similar position and role.  Phase 1 and 2 will require stronger experience covering the preparation of social safeguard documentation for road projects in developing countries using World Bank social safeguard policies.

# 7.	DATA, FACILITIES AND RESOURCES TO BE PROVIDED BY THE EMPLOYER

The following and any other similar data that is available shall be provided by ANE:

Available information in respect of, existing road inventories including data on pavement history and condition, traffic statistics and road accident statistics, geographical maps of all districts including category of road thereon.

ANE will make available electronic copies of relevant road design manuals and specifications.

However, the consultants shall be required to collect any necessary information, which is not available with ANE and shall be responsible for any translation of documents and for processing of data.

# 8.	CONSULTANT’S OBLIGATIONS

## General

The Consultant shall perform the services specified in the “Terms of Reference” under “Scope of Services,” and shall provide the personnel listed under, “Consultant Personnel,” to perform the Services.

The Consultant shall submit to the Client the reports in the form and within agreed time periods specified under “Consultant’s Reports and Documentation

## Transportation Requirements

During the implementation of Phases 1 and 2 of these services, the Consultant will be responsible for the costs and provision of adequate transport for their personnel.

## Staff Housing

During the implementation of the Phases 1 and 2 of these services, the Consultant will be responsible for the costs and provision of adequate accommodation or housing for their project staff.

## Offices for Consultant’s personnel

The consultant shall be responsible for meeting all costs of office provision, operation, supplies, communications, secretarial services, document translation and logistical services during Phases 1 and 2.

## Travel Related Costs and Allowances for Consultant’s personnel

The Consultant is responsible for all travel related costs (tickets, visa cost, medical exams, vaccinations, Covid-19 testing, etcetera) and out of duty station allowances for its personnel.

## Road Surveys

The Consultant is responsible for all staff requirements, equipment and software for undertaking road technical surveys (including FWD), investigations and preparing the OPBRC concept design (topographical surveys, materials testing, geotechnical testing, pavement testing, traffic counting, axle load surveys, CAD (and GIS) design software, meteorological data collection, etcetera) except for those specified under the Provisional Sum.

## Reimbursable Expenditure

The consultant is required to provide evidence of expenditure incurred for all reimbursable expenditure that is to be paid under this Contract. Reimbursement will be made in the currency in which it is incurred or at the exchange rate on the date of purchase.

# 9.	LOGISTICAL SUPPORT

## Liaison Officer

ANE will appoint a liaison officer through whom all requests for information, guidance and assistance should be addressed. All reasonable assistance will be provided, including liaison with other Government departments and access to any relevant data that is not classified as restricted. Other personnel provided will be as agreed during contract negotiations and the kick-off meeting.

ANE shall provide the consultant, without charge, the following:

Assistance in obtaining any required customs clearances, visas and any other official permits, as may reasonably be required;

Such other support facilities as may reasonably be needed for the expeditious performance of the required services, including pertinent files, documents and working papers;

# 10	LOCAL TAXES

Consistent with the provision of the Terms of Agreement, the consulting firm and its expatriate personnel providing services under the contract for which these TOR are written shall be required to pay local taxes on the income and profits derived from these services, unless otherwise provided in the respective contract.

Should the contract require payment of such taxes, it shall also include provision for reimbursement to said firm and its expatriate personnel exclusively for the amounts actually paid subject to the submission of documented evidence. These taxes must be separately identified and detailed in the financial proposal, and if awarded, the contract.

# 11.	PAYMENT SCHEDULE

The services provided under Phase 1 and 2 will be implemented under a lump sum contract and the service provider will receive payments as follows:

1st payment: 10% of the price Contract after presenting the Inception Report of the Project and being approved by the Client as satisfactory;

2nd payment: 20% of the Contract price, after presenting the Interim Report 1 and being approved by the Client as satisfactory;

3rd payment: 20% of the Contract price, after presenting the Interim Report 2 and being approved by the Client as satisfactory;

4th payment: 25% of the Contract price, after presenting the Draft Final Report and being approved by the Client as satisfactory; and

5th payment: 15% of the Contract price, after presenting the Final Conceptual Design Report and the bidding documents for the Project and being approved by the Client as satisfactory.

6th payment: 10% of the Contract price, after approval of the Bid Evaluation Report by the Client.

# ANNEX 1: LOCALITY MAP

Resolução No 68/2020 do Conselho de Ministros de 17 de Novembro de 2020: Política e Estratégia de Segurança Rodoviária (Council of Ministers Resolution No 68/2020 of 17th November 2020: Road Safety Policy and Strategy)

For the purpose of identifying gender gaps among contractors, the consultant shall identify the number of potential bidders that are women led contractors.

The Sample Specifications for OPBRC are available at: https://thedocs.worldbank.org/en/doc/0a3444f756c0adf8dd5e88527f9a1877-0290032021/original/Sample-Specs-OPBRC-April-2021.docx

The latest version of the OPBRC SPD has been prepared for projects which have a high risk for Sexual Exploitation and Abuse (SEA) and/or Sexual Harassment (SH).

For the 94 km road between Metoro to Pemba, there is no previous detailed design. The new design must be made using the consultant’s survey and testing of the current road, along with the client’s desired future service levels that are the same for all sections of the N1 road.

ANE will make available sample data in a data room for bidders to estimate the level of effort required for this activity.

This assessment/appraisal shall also take into consideration potential road safety issues related to wildlife crossings, as these may generate traffic accidents. This might be relevant along Inchope – Gorongosa and Gorongosa – Caia sections, as EN1 alignment along these sections are actually the western and northern limit of a Key Biodiversity Area named “Gorongosa National Park and Marromeu Complex”, while also crossing 4 different Coutadas (hunting concessions).

The SRSEIP was prepared under the World Bank Environmental and Social Framework (ESF). The client has following Bank approved documents that will be shared with bidders: ESMF, RPF, LMP, SA, SEP, ESCP, GBV/SEA/SH Risk Assessment and Mitigation Plan.

Wildlife crossings should be considered if they are relevant road safety issues along N1 (Gorongosa-Marromeu Complex limit).  Appropriate mitigation measures must be considered in the conceptual design work and elaborated as requirements for the project during the implementation phase.

The consultant may indicate in its proposed workplan frequency/timing of such meetings with the E&S consultant.

The Sample Specifications for OPBRC is available on the World Bank's website under https://thedocs.worldbank.org/en/doc/0a3444f756c0adf8dd5e88527f9a1877-0290032021/original/Sample-Specs-OPBRC-April-2021.docx